|  |
| --- |
| Goal 2 Update  3rd Quarter Regional Elected Officials Meeting – September 18, 2019 |
|  |
| Goal 2 |
| DOLA 2020 Census Outreach Grant (HB19-1239) pending – partnered with several municipalities and community organizations to develop extensive outreach strategy focusing on 5 populations. |
| Infographics created to highlight the child care and housing impact in Larimer County. |
| Developing business sector engagement plan – working with United Way and a community member to develop an enhanced business sector engagement plan for objectives 3 and 4. |
|  |
| Objective 1 – Community Health and Well-being |
| Collaboration with County Purchasing and IT to release a Request for Information (June 2019). |
| Service proposal submitted requesting funding to proceed with the implementation of the data tracking/mapping tool. |
| Team working on recommendations to BOCC to define “health and well-being” for Larimer County. |
|  |
| Objective 2 – Employment Opportunities for Individuals with Disabilities |
| Team comprised of two subcommittees; one working on internal County pilot and another focusing on external community programs. |
| Planning activities for October 2019 Disability Awareness Month (October 16th will be Ability Day) |
| Identifying staffing resource to create and implement internal County program. |
|  |
| Objective 3 – Child Care |
| Team has finalized a Steering Committee/Subcommittee structure (see attached). |
| Service proposal requesting funding to conduct a contract data/needs analysis in coordination with housing objective team. |
| Objective team and Talent 2.0 Task Force have been merged into the Steering Committee structure. |
| National Association of Counties Peer Learning Network presentation (9/19/19) |
|  |
| Objective 4 – Housing |
| Conducted extensive research regarding housing services within Larimer County (through municipalities, existing housing authorities), provided by other counties or entities outside Larimer County. |
| Conducted legal research regarding the legal authority for Larimer County. |
| Categorized services and strategies in 4 categories – development/investment, stable housing, unstable housing and supportive services. |
| Service proposal requesting funding to conduct a contract data/needs analysis in coordination with child care objective team. |
| Goal Steward and Objective Leader working with BOCC to revise the Larimer County Housing Authority structure, services and IGA’s. |
| Toured Mission Homes site in Berthoud and will be reviewing Berthoud’s fee restructuring. |
| Partnering with Fort Collins Office of Social Sustainability on mobile home project. |
| Partnering with NoCo Housing Committee. |